## Sheet1
Task / Phase | W1 | W2 | W3 | W4 | W5 | W6
Client Meeting (15th Dec). 1. Minutes recorded. 2. Initial requirements noted. 3. Introduction to 2nd Client part of the Clients Team. | bar: W1 to W2
Supervisor Meeting (17th Dec). 1. Feedback on Timebox 2 and what needs to be done for Timebox 3. 2. Improvements that need to be made were detailed. | bar: W2
Completing and cleaning final Internal PID. | bar: W3
Using verified Client reuirements prepare and optimise the plan,risk and task breakdown. This was done throughout the Christmas period. | bar: W3
Joel and Min was in contact with the client over extra material that was required. This was successfully obtained. This also included client meeting setups | bar: W3
Timebox 3 was begun and that was conducted and put together by everyone which was later merged into one file and submitted. | bar: W3 to W4
Joel contacted the client in regard to a shared folder with all the content needed for the project whilst Min was able to schedule another meeting with the client (remote) for the 15th of January. Following this meeting a consent form was created along with a feedback template and a success criteria for the client to review. | bar: W4 to W5
Planning for supervisor meeting (28th Jan) along with client meeting (29th Jan). 1. Wai-Shing is working on the Tailwind CSS. Along with the enquiries form code. 2. Joel are working on the intial chatbox code. He has also been programming the inital dummy pages. 3. Ahmed is working on a tailored task specific to any work that has been carried out and needing documenting. Along with data research. 4. Min has also been working on the chatbox code. 5. Thomas has been working on formatting and handling the HTML code. 6. Jaime Worked and conducted the Timebox review. | bar: W4 to W6